## Slide 1: Project Status Report Development Phase of Cell Dive Silverlight Migration Reporting period (7th January-2022 to 13th-January-2022)

## Slide 2: Project Status, Key Updates and Attention areas
Key Updates
UAT – In Progress. Bugs/Defects Fixing – In Progress. Testing -In Progress.
Attention Areas
Bugs/Defects – In Progress. Scale Bar – In Progress.
UAT

## Slide 3: Schedule & Workflow
 | Sprint 1 (2 Weeks) | Sprint 2 (2 Weeks) | Sprint 3 (2 Weeks) | Sprint 4 (2 Weeks) | Sprint 5 (2 Weeks) | Sprint 6 (2 Weeks) | Sprint 7 (2 Weeks) | Sprint 8 (2 Weeks)
LTTS-Activities | Requirement updates High level design WCF binding design with new application Evaluation of controls Application skeleton | Application skeleton(contd.) Development of Blazor code Integration of OpenSeaDragon Login implementation WCF code integration Workflow check between applications | Dashboard Navigation Slide manager ImageViewer Loading image and deep zoom Dropdown selection WCF code integration | ImageViewer Image correction Measure-XY Zoom/Rotate Save Multiple Image Viewer Split WCF code integration | ImageViewer Slide navigator Vertical and Horizontal splitting of multiple viewers Swap Viewers Region manager selection Full screen WCF code integration | Image Blending Region manager QC Evaluation WCF code integration | ROI Integrated testing WCF code integration | Packaging & Release support
LTTS-Deliverables | High level design documentation draft Backlog planning | High level design documentation Sprint test report Demo features | Sprint test report Demo features | Sprint test report Demo features Intermediate executable-1 | Sprint test report Demo features | Sprint test report Demo features Intermediate executable-2 | Sprint test report Demo features | Executables Final documentation
LMS | Single point of contact Baselined code Sample images | Single point of contact Demo feedback | Single point of contact Demo feedback | Single point of contact Demo feedback | Single point of contact Demo feedback | Single point of contact Demo feedback | Single point of contact Demo feedback | 
4 Months
1 month of UAT Support by LTTS

## Slide 4: Upcoming MileStones TimeLines
Tentative UAT End Date:
  28th January 2022.

## Slide 5: Critical Issues
Issue | Raised by & Date | Owner | Status (Open / Close) | Resolution/Remediation | Impact if issue not resolved on time | Resolution Required by date
ROI and FOV Optimization | 12th Nov 2021 | LTTS | Closed. | Investigation and Development in Progress | Delay in Schedule | 

## Slide 6: Risk Management
Risk Status | Risk Description | Likely Impact | Impact time frame | Mitigation / Contingency Plan | Risks (Open/ Closed/ Overcome/ Affected & closed) | Remarks
 | Covid-19 related impact on team members | Medium | Ongoing | Team to balance workload in case a team member gets impacted | Open | In India, there is a spike in cases.
 | Hardware for testing the Application | Medium |  | Currently team is testing on their individual machines and allowing LMS team to do the same | Closed | 
 | ROI and FOV Optimization | High | Delayed | Development is completed | Closed | 

## Slide 7: Dependencies on LMS
Dependency | Status | Target Date | Attention required
Confluence access | Dropped |  | 
VPN Access | Completed |  | 
Virtual Machine for testing the Application with real time data | Completed |  | 

## Slide 8: THANK YOU

## Slide 9: Indicators
Guidelines for Risk related indicators
 | On Track
 | Delayed but can be recovered
 | Delayed beyond recovery
Guidelines for Schedule Variation related indicators